## Cover
GREEN FLAG AWARD SYSTEM — REQUIREMENTS SPECIFICATION
Confidential ¦ Keep Britain Tidy x OJ Solutions / Alliance Knights IT Limited
DOCUMENT INFORMATION
Document Title | Green Flag Award System — Requirements Specification
Version | 1.1
Status | Draft — Pending KBT Sign-Off
Date | 8 April 2026
Prepared by | Rae (Raemelu Imasiku), Project Manager — OJ Solutions
Reviewed by | Jonathan Falade, Managing Director — OJ Solutions
Approved by | Pending — KBT Product Owner [to be confirmed by Anthony]
Classification | Confidential — KBT and OJ Solutions only
PURPOSE
This Requirements Specification is the single source of truth for the Green Flag Award System rebuild. It defines what will be designed, built, tested, and delivered. Every design decision Oya makes references this document. Every feature Richard builds is tested against the acceptance criteria here. Every deliverable KBT approves is signed off against a section of this document. This document is version-controlled. Changes after KBT sign-off require a formal Change Request.
HOW TO USE THIS DOCUMENT
KBT | Read each section. Sign-off blocks require approval from the KBT Product Owner before the relevant build begins. Once signed, requirements are frozen — changes require a Change Request. Items marked "Pending KBT Input" need a decision or document from you before that feature can be built.
OJ Solutions — Design | Every screen maps to a Requirement ID (format: REQ-[AREA]-[NNN]). Read Sections 02 and 03 before opening any design tool. Design Principles are non-negotiable.
OJ Solutions — Build | Every feature has a Requirement ID. Acceptance criteria define what "done" means. Non-functional targets in Section 04 define performance, security, and accessibility standards.
SECTIONS
01 — Glossary | Every term defined. Shared language for the team and the client.
02 — Design Principles | 15 non-negotiable rules for every design and build decision.
03 — Functional Requirements | What the system shall do. Testable statements with acceptance criteria and Requirement IDs.
04 — Non-Functional Requirements | How well the system performs. Performance, security, accessibility, availability.
05 — Award Type Specifications | All four award tracks: Green Flag, Community Award, Green Heritage, Group Award.
06 — Role Profiles & Permissions | 9 user roles. Full permission matrix.
07 — Judge Types & Allocation Rules | 6 judge types. Allocation algorithm. Conflict of interest rules.
08 — Form Field Specifications | Every field in every form with validation and help text.
09 — Document Requirements | File types, sizes, re-upload rules, URL link option.
10 — Status & RAG System | 46 status values across all entities.
11 — Notification Matrix | Every system notification with trigger, recipient, and timing.
12 — Screen Map | Every screen with entry point, data, and error states.
13 — Decision Logic | Every business rule and branching point.
14 — Key Dates by Country | Application windows, payment deadlines, announcement dates.
15 — Client Data Requirements | Everything KBT must provide before build.
16 — Technical Integration Spec | What3Words, OS Greenspace, Stripe, Business Central, SMS.
17 — Process Flows | Current state vs new platform for all user types.
18 — User Stories | All user stories with acceptance criteria.
19 — Open Items & Assumptions | Pending decisions and working assumptions for KBT to confirm.
VERSION HISTORY
v1.0 ¦ 31 March 2026 | Initial draft from requirements gathering session at KBT offices. Captured by Rae (OJ Solutions).
v1.1 ¦ 8 April 2026 | Technical architecture incorporated. What3Words, OS Greenspace, dual application window, and judge allocation engine design added. Open questions from technical analysis included.
IMPORTANT DATES
Bank Holidays | Good Friday 4 April and Easter Monday 7 April — no working days.
First response requested | Tuesday 8 April 2026
Sprint 1 target start | 14 April 2026 — critical items from KBT needed before this date.
Target go-live | July 2026

## 01 Glossary
SECTION 01 — GLOSSARY ¦ Every Term Defined
The shared language of this project. Every term defined to prevent ambiguity across design, build, and client communication.
# | Term | Type | Definition | Used In | Do Not Confuse With
PROGRAMME
1 | Green Flag Award | Programme | International quality award for parks and green spaces. Administered by KBT under MHCLG licence until 2030. 2,250+ UK parks awarded in 2025. | Entire platform | Community Award (separate track)
2 | Full / Announced Assessment | Assessment | Announced site visit. Judge reviews management plan then visits. Park knows visit is happening. Old term: Full judging. | Flows, mobile app, allocation | Mystery Shop
3 | Mystery Shop / Unannounced | Assessment | Unannounced site visit. Judge visits as member of public. Park never knows until result published. No management plan review. | Flows, notifications, allocation | Full Assessment
4 | Group Award | Assessment | Distinct track for organisations managing 10+ parks. Organisation-level assessment. Peer review every 2 years. Mystery shops per site annually. Deep dive session required. | Group Award flow (TBC) | Full Assessment
5 | Green Heritage Accreditation | Award type | Additional accreditation bolt-on for historic sites. Requires Green Flag Award first. Heritage criteria assessed alongside standard. J-04 judge required. | Application form, allocation | Green Flag Award standard
6 | Community Award | Award type | Distinct award with 24 criteria. Different scoring model. J-03 judge required. Separate application form. | Application form, scoring | Green Flag Award standard
7 | Desk Assessment | Component | Review of management plan before site visit. Scored out of 30. Criterion 8 of full assessment. Minimum passing score: 15. | Scoring, judge app | Site Assessment
8 | Site Assessment | Component | Physical on-site evaluation. Scored out of 70. Criteria 1-7. Minimum: 42. Overall minimum: 66. | Scoring, judge app | Desk Assessment
9 | Award Cycle | Concept | Annual cycle from application window open to result announcement. Different countries may run different schedules. | Data model, key dates | Calendar year
10 | Assessment Episode | Data | A single judging event for a park in a given cycle. Type: full_assessment or mystery_shop. A park can have two episodes from different cycles active simultaneously. | Data model, status system | Application
11 | Application | Data | What a park applicant submits. Only exists for Full Assessment episodes. Contains management plan, site details, payment reference. Mystery Shop has no application. | Application form, data model | Assessment Episode
12 | Management Plan | Document | Site-specific document: site condition, community wants, action plan. Required for Full Assessment. Upload as file or URL link. | Application form, documents | Management Plan template (guidance KBT provides)
13 | Band Score | Scoring | Score shown to applicants. Banded version of raw sub-criterion scores. Prevents year-on-year comparison disputes. Exact bands TBC with KBT. | Results display | Raw score (internal)
14 | Dual Application Window | Technical | State where two award cycle windows are active simultaneously — prior year mystery shop carryover alongside current year full assessment. | Data model, architecture | Single window (current system limitation)
USER ROLES
15 | Super Admin | Role | Maximum system authority. All countries. All configuration. No developer involvement needed. Maximum 2 people. | Role profiles | KBT Admin
16 | KBT / Country Admin | Role | Day-to-day operational admin. Scoped to assigned countries. Handles registrations, applications, allocations, decisions. | Role profiles | Super Admin
17 | Organisation Admin | Role | NEW. Admin at managing organisation level (e.g. council). Sees all their parks. Can request new parks. | Org dashboard | Park Manager
18 | Park Manager | Role | Manages a specific park site. Applies for award, uploads documents, views status, downloads certificate. | Park portal | Organisation Admin
19 | Judge / Assessor | Role | Volunteer conducting site assessments. Uses mobile app on site. Sees allocated sites only. | Judge portal, mobile app | KBT Admin
20 | Primary Judge | Role | Lead judge. Starts scoring form. Coordinates visit date. | Allocation engine | Secondary Judge
21 | Secondary Judge | Role | Supporting judge. Assists on 2-judge assessments. Both must accept before park is notified (Full only). | Allocation engine | Primary Judge
TECHNICAL
22 | COI — Hard Block | Technical | Conflict of interest that absolutely prevents assignment. Cannot be overridden. Same employer, self-declared personal connection. | Allocation engine | COI Soft Flag
23 | COI — Soft Flag | Technical | Conflict of interest noted and shown to admin but does not auto-block. Adjacent local authority. Admin acknowledges and decides. | Allocation engine | COI Hard Block
24 | Rotation Rule | Technical | Same judge should not assess same park in consecutive Full Assessment years. Not a hard block — waivable in rural areas. | Allocation algorithm | Conflict of Interest
25 | Cluster Allocation | Technical | Assigning a judge to multiple geographically compact parks for efficiency. | Allocation, map view | Individual allocation
26 | What 3 Words | Integration | Maps every 3m² on earth to a unique 3-word address. Used for precise park entrance location and judge navigation. | Registration, judge portal | Postcode
27 | OS Open Greenspace | Data source | Ordnance Survey dataset with polygon boundaries for parks across GB. Used to suggest park size on registration. | Park registration | ONS Open Geography (different — covers National Parks only)
28 | Business Central | Integration | KBT finance system. Portal sends invoice data to Business Central. Integration format TBC with KBT Finance. | Invoicing | Stripe (payment gateway)
29 | Stripe | Integration | Payment gateway for online card payments. Replaces current PayPal workaround. | Payments | Business Central (finance system)
30 | MHCLG | Organisation | Ministry of Housing, Communities and Local Government. Holds the Green Flag Award licence. Requires annual reporting. | Reporting, key dates | KBT
31 | WCAG 2.1 AA | Standard | Web Content Accessibility Guidelines level AA. Legal accessibility standard. Affects contrast, keyboard navigation, screen readers. | Non-functional requirements | WCAG AAA (higher standard — not required)
32 | LANTRA | Body | Accredits Green Flag Award judges. Judges must hold current LANTRA accreditation to be eligible for allocation. | Judge profile, allocation | IHBC, Historic England
33 | MoSCoW | Method | Must Have / Should Have / Could Have / Won't Have. Prioritisation framework for all requirements. | Functional requirements | Sprint planning
34 | SPF/DKIM | Technical | Email authentication protocols. Correct configuration prevents council firewalls blocking platform emails — a critical known issue. | Email deliverability | Email content
SIGN-OFF — 01 — Glossary
Prepared by | Rae (Raemelu Imasiku) — Project Manager, OJ Solutions
Reviewed by | Jonathan Falade — Managing Director, OJ Solutions
Approved by (KBT) | [KBT Product Owner — TBC]
Date approved | ____________
Version | 1.1

## 02 Design Principles
SECTION 02 — DESIGN PRINCIPLES ¦ 15 Non-Negotiable Rules
These are not guidelines. They are constraints. Every design decision and architectural choice is tested against them.
# | Principle | Category | What it means in practice | Why it matters here | How it is tested
USER EXPERIENCE
1 | Mobile first, always | UX | Every screen designed for 375px phone first. Desktop enhances. Never defines. All Figma frames start at 375px. | Judges assess in parks on phones. Paul confirmed mobile-first mandate explicitly. | All screens reviewed on real device before sprint sign-off. No horizontal scrolling on mobile.
2 | Design for low digital confidence | UX | Assume the user cannot cut and paste. Large tap targets (min 44px). Error messages say what to do — not just what went wrong. Labels on every field. | Paul: "Don't get technical with me." Some users scan documents because they don't know how to attach files. These users are paying customers. | User testing includes at least one non-technical participant per sprint. Any journey requiring 3+ attempts = redesign.
3 | Simple over clever | UX | If a feature requires a walkthrough, redesign it. Every primary action: 3 taps or clicks maximum on mobile. No hidden menus for core actions. | Paul said explicitly: keep it as simple as possible. Platform handed to other countries — if it cannot be explained in 10 minutes it is too complex. | Core journeys tested with first-time users. Complexity measured. If over 3 attempts to complete = P1 design defect.
4 | Show progress, always | UX | Users always know where they are, what they have done, and what they need to do next. Every multi-step form has a progress indicator. Every entity has a visible status. | Parks phone KBT repeatedly because they have no visibility. Judges accept sites and hear nothing. This drives the entire volume of manual KBT contact. | Every entity status visible without contacting KBT. UAT pass criterion: user determines status without help.
5 | Context-sensitive UI | UX | Show only what is relevant. First-time parks see Apply for Award — not six tabs. Mystery shop parks see nothing different. Returning parks see pre-populated forms. | Current system shows all options to everyone. Parks navigate to wrong sections. Mystery shop is compromised. | Role-based access testing confirms correct screen scope per user type.
ACCESSIBILITY
6 | WCAG 2.1 AA minimum | Accessibility | All colour combinations pass AA contrast ratios. All images have alt text. All forms keyboard-navigable. All interactive elements screen-reader accessible. | Legal requirement under Equality Act and Public Sector Accessibility Regulations. Green spaces are public — the platform must be inclusive. | Automated Axe audit before every sprint demo. Zero critical accessibility violations permitted in production.
7 | Accessible on assistive technology | Accessibility | All core journeys completable using only a keyboard. All interactive elements have accessible names. Compatible with NVDA + Chrome and VoiceOver + Safari. | Parks may be managed by people with disabilities. Cannot exclude them. | Manual screen reader test on core journeys before UAT.
INTERNATIONAL
8 | No UK assumptions baked in | International | No hardcoded UK address formats or field labels. All geography labels configurable. Distances in miles or km per country. All dates ISO in the database. | System is deployed in UAE, Australia, and expanding. Building UK-only and retrofitting costs 3x as much as building international from day one. | International admin runs entirely without UK-specific fields appearing. Verified before go-live.
9 | Language-ready architecture | International | All user-facing strings stored separately from code. Welsh language support possible without a code change. | Welsh legal requirements may apply. Canada needs English and French. UAE needs Arabic RTL. | String externalisation confirmed by Richard before Sprint 1 closes.
PERFORMANCE
10 | Perceived speed over actual speed | Performance | Skeleton screens shown immediately. Data loads progressively. Progress bars on uploads. Long operations in background. | Admin managing 1,800 applications cannot wait 10 seconds for a list. Judges on poor signal need the app to feel responsive. | Every page shows meaningful content within 1 second. Measured in Lighthouse.
DATA & PRIVACY
11 | Minimum necessary data only | GDPR | Collect only data with a stated purpose. Every form field justified against a use case. No "just in case" fields. | GDPR data minimisation principle. DPA must be signed before build. DPIA required. | Every form field has a stated purpose in Form Field Specifications. Data audit before go-live.
12 | Personal data never displayed unnecessarily | GDPR | Assessor details not shown to parks until both have accepted. Park contact details not public unless chosen. DBS data never in bulk exports. | GDPR data protection by design. Park managers have been harassed when personal details were too public. | Privacy review of every screen before UAT.
SYSTEM INTEGRITY
13 | The system enforces rules — humans cannot bypass | Rules | Payment deadlines, window closes, and mystery shop suppression enforced at API level — not just UI. The wrong thing must be impossible, not just discouraged. | Current system relies on human memory for mystery shop suppression. It fails. New system makes the wrong action impossible. | All business rules verified in API-level tests, not just UI tests.
14 | Audit everything | Security | Every action that changes data is logged: who, when, what changed. Logs are immutable. Cannot be edited by anyone including Super Admin. | Legal protection. GDPR accountability. Ability to investigate complaints and prove decisions. | Audit log entry verified for every data-changing action in each sprint.
15 | Fail safely and informatively | Reliability | When something fails, user told clearly: what happened, what to do next, whether data was saved. No silent failures. No data loss on network drop. | Judges completing assessments on poor signal cannot lose their work. Parks submitting plans cannot lose uploads. | Error handling spec required for every form and upload. Offline sync tested in Sprint 2.
SIGN-OFF — 02 — Design Principles
Prepared by | Rae (Raemelu Imasiku) — Project Manager, OJ Solutions
Reviewed by | Jonathan Falade — Managing Director, OJ Solutions
Approved by (KBT) | [KBT Product Owner — TBC]
Date approved | ____________
Version | 1.1

## 03 Functional Requirements
SECTION 03 — FUNCTIONAL REQUIREMENTS ¦ What the System Shall Do
Every requirement is a testable statement with a unique ID, MoSCoW priority, and acceptance criteria. KBT signs off each section.
REQ ID | Area | MoSCoW | User Role | The system SHALL... | Acceptance Criteria — how we know it is built correctly | Screen Ref | Story Ref | Status
REGISTRATION
REQ-REG-001 | Registration | M | Park Manager | Allow a park manager to complete an online registration form with built-in eligibility validation (publicly accessible, free to enter, minimum size). Form stops with a specific reason if any eligibility criterion fails. | 1. Eligibility check on submission. 2. Form stops with specific reason on failure. 3. Successful submission creates PENDING_VERIFICATION account. 4. Confirmation email sent within 60 seconds. 5. KBT admin receives notification. | SCR-REG-01 | US-REG-001 | Confirmed
REQ-REG-002 | Registration | M | System | Send email verification link immediately on registration. Account must not progress to admin review until verified. Unverified accounts purged after 7 days with a day-5 reminder. | 1. Email sent within 60 seconds. 2. Click sets email_verified=true. 3. Day-5 reminder sent. 4. Purge at exactly 7 days. 5. Re-registration allowed after purge. | SCR-REG-02 | US-REG-002 | Confirmed
REQ-REG-003 | Registration | M | System | Check park name and address for duplicates on registration. Warn user and alert admin if a match exists. Does not block — requires acknowledgement. | 1. Name check on submit. 2. Address check on postcode entry. 3. Warning shown if match — requires acknowledgement. 4. Admin alert sent. | SCR-REG-01 | US-REG-003 | Confirmed
REQ-REG-004 | Registration | M | KBT Admin | Present admin with a structured registration review queue. Approve or reject with reason. All actions generate automated emails to the park. | 1. Approved: account ACTIVE, welcome email with portal link sent. 2. Rejected: rejection email with specific reason. 3. Both create audit log entries. | SCR-ADM-02 | US-ADM-001 | Confirmed
REQ-REG-005 | Registration | M | System | Auto-fill address fields when valid postcode is entered. Validated against UK postcode database. Manual entry fallback for international applicants. | 1. Valid postcode auto-fills address, town, county. 2. Invalid postcode shows clear error. 3. Manual fallback available. 4. International formats accepted. | SCR-REG-01 | US-REG-004 | Confirmed
REQ-REG-006 | Registration | M | System | Integrate What 3 Words for park entrance location. Store both W3W address and lat/lng. Display W3W deeplink to judges for navigation. Postcode used only to centre map initially. | 1. W3W widget on location step. 2. W3W or pin sets both fields. 3. Judge sees https://w3w.co/[address] as clickable link. 4. Both stored in DB. | SCR-REG-01 | US-REG-005 | Confirmed
REQ-REG-007 | Registration | S | System | When applicant drops a location pin, run a spatial query against OS Open Greenspace data to suggest the park name and size. Applicant must confirm — never auto-populate without confirmation. | 1. Pin drop triggers spatial query within 200m. 2. Top 3 matches shown as suggestions. 3. Applicant selects or dismisses. 4. Confirmed size populates size field. 5. International/NI parks: manual entry only. | SCR-REG-01 | US-REG-006 | Confirmed
REQ-REG-008 | Registration | M | System | Auto-populate local authority name, region, country, and parliamentary constituency from the dropped pin location using ONS API. Eliminates free-text entry of these fields. | 1. Pin drop triggers ONS API call. 2. LA name, region, country, constituency populated. 3. Fields editable if auto-populated value incorrect. 4. Audit note if manually overridden. | SCR-REG-01 | US-REG-007 | Confirmed
APPLICATION FORM
REQ-APP-001 | Application | M | Park Manager | Save application progress after every field change. Application submitted with or without management plan. Management plan uploadable after submission until judge is allocated. | 1. Each field saved on change. 2. Partial application shown as DRAFT. 3. Park can return and continue. 4. Management plan uploadable post-submission until allocation. | SCR-PRK-03 | US-APP-001 | Confirmed
REQ-APP-002 | Application | M | Park Manager | Support management plan upload as direct file (PDF/Word/PPT, up to 50MB via chunked upload) AND as URL link (Google Drive, SharePoint, OneDrive). Both options on the same form. | 1. File: PDF/DOCX/PPTX accepted. 2. Files over 5MB use chunked upload with progress bar. 3. Files over 50MB show URL option automatically. 4. URL: accessibility checked on submission. | SCR-PRK-03 | US-APP-002 | Confirmed
REQ-APP-003 | Application | M | System | When management plan is re-uploaded, check file content hash — not filename — to determine if genuinely changed. Warn if identical. Confirm replacement if different. Archive previous version. | 1. SHA-256 hash computed on upload. 2. Compared to stored hash. 3. Identical: warning shown. 4. Different: silent replacement, previous archived. 5. Version history accessible to admin. | SCR-PRK-03 | US-APP-003 | Confirmed
REQ-APP-004 | Application | M | System | Enforce application window dates at API level. Submissions rejected by server after close date regardless of UI. Super Admin override with mandatory reason creates audit log entry. | 1. Server checks cycle dates before accepting submission. 2. Out-of-window: clear error with next window date. 3. Super Admin override: mandatory reason, audit log. | SCR-PRK-03 | US-APP-004 | Confirmed
REQ-APP-005 | Application | M | System | Pre-populate application form for returning parks with previous year's data. All fields editable. Only payment section is cleared on annual reset. | 1. Returning park sees previous data pre-filled. 2. All fields editable. 3. Previous management plan shown as reference. 4. Payment section blank. | SCR-PRK-03 | US-APP-005 | Confirmed
REQ-APP-006 | Application | M | System | Show live progress indicator on park dashboard and application form. Admin views in-progress applications with completion percentage without impersonating the park. | 1. Progress bar on dashboard and form. 2. Admin dashboard shows in-progress with %. 3. Admin views from admin panel — no impersonation. | SCR-PRK-02 | US-APP-006 | Confirmed
REQ-APP-007 | Application | M | Park Manager | Provide a structured page for parks to respond to the previous year's judge feedback. Response visible to judges in subsequent years. Not a document upload — typed directly into the system. | 1. Dedicated page in application form. 2. Previous year's judge feedback displayed. 3. Park types response. 4. Response visible to judges in their site preparation view. | SCR-PRK-03 | US-APP-007 | Confirmed
ASSESSMENT CYCLE
REQ-CYC-001 | Cycle | M | System | Automatically determine assessment type for each returning park per cycle year: Full to Mystery, Mystery to Full. New sites and failed sites always receive Full. Configurable per country. | 1. cycle_type set on application submission. 2. Full last year: MYSTERY set. 3. Mystery last year: FULL set. 4. New/failed: FULL set. 5. Country-level alternation rules configurable by Super Admin. | SCR-ADM-01 | US-CYC-001 | Confirmed
REQ-CYC-002 | Cycle | M | System | Suppress ALL park-facing notifications when a park is in a mystery shop year. Park sees only APPLICATION_UNDER_REVIEW throughout. No assessor name, visit date, or assessment type revealed at any point. | 1. Suppression flag set when cycle_type=MYSTERY. 2. All park assignment notifications blocked at server. 3. Park sees APPLICATION_UNDER_REVIEW only. 4. Admin can see suppressed notification log. | SCR-ADM-05 | US-CYC-002 | Confirmed
REQ-CYC-003 | Cycle | M | System | Support two active award cycle windows simultaneously. Prior year mystery shop carryover and current year full assessment can coexist. Each park has at most one episode per type per cycle year. | 1. Data model supports two active cycles. 2. Mystery shop episode from 2025 cycle and Full Assessment episode from 2026 cycle coexist for same park. 3. Park dashboard shows both with distinct status badges. | SCR-ADM-01 | US-CYC-003 | Confirmed
JUDGE ALLOCATION
REQ-ALO-001 | Allocation | M | System | Auto-suggest judge count per assessment: 2 judges for new sites, >25 hectares, heritage, and failed sites. 1 judge for passed sites under 25 hectares. Option for 3rd judge for training. Admin can override with reason. | 1. requires_second_judge calculated from park size and history. 2. Suggested count shown on allocation screen. 3. Admin override with mandatory reason. 4. Override logged. | SCR-ADM-06 | US-ALO-001 | Confirmed
REQ-ALO-002 | Allocation | M | System | Filter judge candidates to exclude hard COI judges before showing allocation options. Soft COI judges shown with visible flag requiring admin acknowledgement. | 1. Hard COI judges do not appear. 2. Soft COI judges appear with amber flag and reason. 3. Admin must acknowledge flag to proceed. 4. Both logged. | SCR-ADM-06 | US-ALO-002 | Confirmed
REQ-ALO-003 | Allocation | M | System | Apply 2-year rotation rule: judge who assessed same park in previous Full Assessment year is deprioritised. Override allowed in rural areas with mandatory reason. | 1. Rotation flag shown on deprioritised candidates. 2. Shown at bottom of list. 3. Override with mandatory reason. 4. Override logged. | SCR-ADM-06 | US-ALO-003 | Confirmed
REQ-ALO-004 | Allocation | M | System | Display map view on judge allocation screen showing all parks in selected area with allocation status. Admin identifies geographic clusters and assigns nearby parks to same judge. | 1. Map on allocation screen. 2. Parks coloured by status. 3. Clicking park opens allocation panel. 4. Judge's other allocations visible. | SCR-ADM-06 | US-ALO-004 | Confirmed
REQ-ALO-005 | Allocation | M | System | Hold judge emails in batch. Admin allocates without sending emails. Release on demand or at a scheduled date/time. | 1. Allocation saved without emails. 2. Dashboard shows pending unreleased. 3. Release now or schedule. 4. On release: all batch emails sent simultaneously. | SCR-ADM-06 | US-ALO-005 | Confirmed
REQ-ALO-006 | Allocation | M | System | When both judges accept a Full Assessment allocation, reveal judge contact details to the park contact and enable in-platform messaging. | 1. Both accepted: park sees judge names and can message. 2. One accepted: no reveal. 3. Mystery shop: never reveal. 4. All comms via platform. | SCR-PRK-05 | US-ALO-006 | Confirmed
SCORING & RESULTS
REQ-SCR-001 | Scoring | M | System | Calculate scores automatically from sub-criterion inputs. Flag to admin if desk assessment below 15, field below 42, or overall below 66. Admin must acknowledge threshold breach before awarding. | 1. Score calculated on each entry. 2. Running totals visible to judge. 3. Threshold flags shown in red. 4. Admin must confirm acknowledgement to award below threshold. | SCR-ADM-07 | US-SCR-001 | Confirmed
REQ-SCR-002 | Scoring | M | System | Show applicants band scores only. Individual sub-criterion scores visible to admin and judges only. Band definitions to be confirmed by KBT. | 1. Park portal shows band not raw score. 2. Admin and judge see full raw scores. 3. Band definitions applied consistently. | SCR-PRK-06 | US-SCR-002 | Pending KBT Input
REQ-SCR-003 | Scoring | M | Judge | Capture scores, notes, and photos for each criterion via mobile app during site visit. Voice notes transcribed automatically. Auto-save after every input. Works offline. | 1. Assessment form loads offline-capable. 2. Photo tagged to criterion. 3. Voice note transcribed within 60 seconds. 4. Auto-save confirmed after every entry. 5. Syncs when connection restored. | SCR-MOB-02 | US-SCR-003 | Confirmed
REQ-SCR-004 | Results | M | System | Hold Full Assessment results until admin triggers batch release on announcement date. Mystery shop results released individually and immediately on admin confirmation. | 1. Full: status=CONFIRMED_HELD until release. 2. Admin sets date/time. 3. At set time: all CONFIRMED_HELD publish. 4. Mystery shop: publishes immediately on confirmation. | SCR-ADM-08 | US-SCR-004 | Confirmed
REQ-SCR-005 | Results | M | System | Automatically update the public map on result release. Parks that pass: pin appears/remains. Parks that fail: pin removed. No manual admin step. | 1. Result publish updates parks.current_status. 2. Map reflects new status within 60 seconds. 3. No admin action needed for map update. | SCR-PUB-01 | US-SCR-005 | Confirmed
REQ-SCR-006 | Scoring | M | Judge | If a judge scores a criterion below a threshold, the recommendations field for that criterion becomes mandatory before submission. Cannot submit with low score and empty recommendation. | 1. Low score triggers mandatory recommendations field. 2. Submission blocked until completed. 3. Specific message: "Score of [X] requires improvement recommendations." | SCR-MOB-02 | US-SCR-006 | Confirmed
PAYMENTS
REQ-PAY-001 | Payments | M | System | Generate invoice automatically when application is submitted. Invoice sent by email and available in park portal within 30 seconds. All UK VAT invoice legal requirements met. | 1. Invoice within 30 seconds of submission. 2. Includes: KBT legal name, VAT number, invoice number, fee, VAT, total, due date, payment instructions. 3. Email sent. 4. Available in portal. | SCR-ADM-09 | US-PAY-001 | Confirmed
REQ-PAY-002 | Payments | M | System | Block assessment progression if payment not confirmed by configured deadline (end of March). Enforced at system level. Only Super Admin can override with documented reason. | 1. Daily job checks payment vs deadline. 2. Unpaid by deadline: PAYMENT_OVERDUE set, assessment blocked, park notified. 3. Super Admin override: mandatory reason, audit log. | SCR-ADM-09 | US-PAY-002 | Confirmed
REQ-PAY-003 | Payments | M | Park Manager | Support PO number entry, online card payment via Stripe, and "we do not use purchase orders" option. Application submittable with PO pending. | 1. PO field: free text. 2. No-PO checkbox available. 3. Stripe card payment present. 4. Can submit without payment confirmed. 5. Both routes logged. | SCR-PRK-04 | US-PAY-003 | Confirmed
JUDGE PORTAL
REQ-JDG-001 | Judge Portal | M | Judge | Fully mobile-responsive judge portal. Functional on iOS 15+ and Android 11+. All core actions in 3 taps on mobile. | 1. Loads correctly at 375px (iPhone SE). 2. All actions completable without horizontal scroll. 3. Text readable without zoom. 4. Tap targets minimum 44px. | SCR-JDG-01 | US-JDG-001 | Confirmed
REQ-JDG-002 | Judge Portal | M | Judge | Submit expense claims per site within portal. Unlocks after feedback report submitted. Visible status to judge. | 1. Expense form available per allocation after feedback submitted. 2. Fields: travel, distance, accommodation, receipts. 3. Submitted to KBT admin. 4. Status visible to judge. | SCR-JDG-04 | US-JDG-002 | Confirmed
REQ-JDG-003 | Judge Profile | M | System | Three judge status levels: Untrained, Training, Experienced. System generates admin task when upgrade conditions met. Admin approves. Judge notified. | 1. Upgrade conditions detected by system. 2. Admin task created. 3. One-click approve. 4. Judge notified on upgrade. | SCR-ADM-12 | US-JDG-003 | Confirmed
NOTIFICATIONS
REQ-NOT-001 | Notifications | M | KBT Admin | All email templates editable by KBT admin in the platform. No developer involvement needed. | 1. Template management screen in admin. 2. All templates listed with trigger event. 3. WYSIWYG editor. 4. Preview function. 5. Changes immediate. | SCR-SA-04 | US-NOT-001 | Confirmed
REQ-NOT-002 | Notifications | M | System | Send SMS backup notifications for judge allocation events where email is frequently blocked. Events: new allocation, day-3 reminder, day-7 reminder. | 1. SMS on allocation. 2. Day-3 SMS if not accepted. 3. Day-7 SMS if not accepted. 4. Brief message linking to portal. | — | US-NOT-002 | Confirmed
REQ-NOT-003 | Notifications | M | System | Automated renewal reminder sequence: 60, 30, 14, and 7 days before certificate expiry. Runs without manual admin action. | 1. Daily job checks expiry dates. 2. Reminder at each milestone if not already sent. 3. Duplicate-send prevention per certificate. 4. Admin dashboard shows renewal pipeline. | — | US-NOT-003 | Confirmed
SECURITY
REQ-SEC-001 | Security | M | All Users | MFA for all admin accounts. Recommended for parks and judges. Method: email link (no code copying). Device remembered 30 days after successful verification. | 1. Admin/Super Admin: MFA required to log in. 2. Email link within 15 seconds. 3. Link expires after 10 minutes. 4. Device remembered 30 days. 5. Parks/judges: MFA offered as optional. | SCR-AUT-01 | US-SEC-001 | Confirmed
REQ-SEC-002 | Security | M | System | Immutable audit log for every data-changing action. Records: user, role, action, entity, before/after state, timestamp UTC, IP. Cannot be edited or deleted by anyone. | 1. Every data change creates audit entry. 2. Table is append-only. 3. Super Admin can view and export, not modify. 4. Failed logins logged. 5. Bulk exports logged. | SCR-SA-04 | US-SEC-002 | Confirmed
SIGN-OFF — 03 — Functional Requirements
Prepared by | Rae (Raemelu Imasiku) — Project Manager, OJ Solutions
Reviewed by | Jonathan Falade — Managing Director, OJ Solutions
Approved by (KBT) | [KBT Product Owner — TBC]
Date approved | ____________
Version | 1.1

## 04 Non-Functional Reqs
SECTION 04 — NON-FUNCTIONAL REQUIREMENTS ¦ How Well the System Performs
Performance, availability, security, accessibility, and reliability. These are not optional extras. A system that works but is slow or inaccessible is not a delivered system.
NFR ID | Category | Name | Target — the measurable specification | How it is measured | Rationale | MoSCoW
PERFORMANCE
NFR-PER-001 | Performance | Page load time | Any page must load and display meaningful content within 2 seconds at P95, under 200 concurrent users. | Google Lighthouse score >= 85. Load tested with k6 before go-live. | Admin managing 1,800 applications cannot wait. Parks abandon slow forms. | M
NFR-PER-002 | Performance | API response time | All API endpoints respond within 500ms at P95 under normal load (up to 500 concurrent users). Bulk operations may take up to 30 seconds but must show progress. | AWS CloudWatch monitoring. P95 per endpoint. | Slow APIs make the whole UI feel broken. | M
NFR-PER-003 | Performance | Offline mobile capability | Judge mobile app functions fully offline: scoring, photo capture, note entry. Data syncs automatically on reconnection. Zero data loss on connection drop. | Manual test: complete full assessment in flight mode. Reconnect. Verify sync and data integrity. | Judges assess in rural parks. Poor signal is the norm, not the exception. | M
NFR-PER-004 | Performance | File upload | Files up to 50MB upload with visible progress bar via chunked upload. Failure shows clear retry — data not lost. | Test 50MB PDF on throttled 4G. Progress bar visible. Retry confirmed. | Management plans are often over 10MB. Silent upload failure causes abandonment. | M
AVAILABILITY
NFR-AVL-001 | Availability | Uptime | 99.5% uptime monthly excluding approved maintenance. During judging season (April-June) and announcement (July): zero unscheduled downtime target. | Monthly uptime report from host. Incidents logged. | Downtime on announcement day is a public reputational failure. | M
NFR-AVL-002 | Availability | Maintenance windows | 01:00-05:00 UTC weekdays only. 48 hours minimum notice to KBT before any scheduled maintenance. | Schedule agreed with KBT before go-live. Status page updated. | Judges may submit assessments at any hour. International time zones. | M
NFR-AVL-003 | Availability | Backup | Database backed up hourly to separate location. File storage backed up daily. Retained 30 days minimum. | Backup schedule configured and verified before go-live. Restore test conducted. | GDPR accountability. KBT data cannot be lost. | M
SECURITY
NFR-SEC-001 | Security | Encryption at rest | All database data encrypted at rest (AES-256). All file storage encrypted. Keys via AWS KMS. | Infrastructure security review before go-live. Penetration test includes storage. | GDPR: appropriate technical measures to protect personal data. | M
NFR-SEC-002 | Security | Encryption in transit | All data via TLS 1.2 minimum (TLS 1.3 preferred). HTTPS enforced everywhere. HSTS enabled. No HTTP endpoints in production. | SSL Labs A rating before go-live. HSTS verified. | Legal obligation. Personal data in transit. | M
NFR-SEC-003 | Security | Penetration testing | Independent third-party pen test before go-live. All critical and high findings resolved before launch. Medium findings have documented remediation plan. | Pen test report provided. Critical/high = zero before go-live. | KBT holds personal data of thousands. A breach is reputational and legal disaster. | M
NFR-SEC-004 | Security | Rate limiting | Auth endpoints: 5 attempts/min/IP. API endpoints: 100 requests/min/user. Certificate verification: 60/min/IP. | Rate limits verified in load test. 429 response confirmed. | Prevents brute force and scraping. | M
NFR-SEC-005 | Security | Session management | Sessions expire after: 15 min (Super Admin), 30 min (KBT Admin), 60 min (Parks, Judges). Tokens invalidated on logout. | Session expiry tested per role. Token invalidation on logout verified. | Admin sessions on shared machines are a security risk. | M
ACCESSIBILITY
NFR-ACC-001 | Accessibility | WCAG 2.1 AA | Full platform meets WCAG 2.1 Level AA. Colour contrast >= 4.5:1 (normal text), >= 3:1 (large text). All images have alt text. All forms keyboard-navigable. | Automated Axe audit on every screen before sprint sign-off. Manual keyboard test. Screen reader test (NVDA + Chrome, VoiceOver + Safari). | Legal requirement. Green spaces are public — the platform must be inclusive. | M
NFR-ACC-002 | Accessibility | Touch targets | All interactive elements on mobile: minimum 44x44px touch target. No interactive elements within 8px of another. | Touch target audit via Chrome DevTools mobile emulation. | Low digital confidence and motor difficulties require larger targets. | M
BROWSER SUPPORT
NFR-BRW-001 | Browser | Web browsers | Works correctly on: Chrome, Safari, Firefox, Edge — last 2 major versions each. Internet Explorer: not supported. | Cross-browser test suite before go-live. All core journeys on each browser. | Councils default to Edge. Varied browser landscape. | M
NFR-BRW-002 | Browser | Mobile OS — Judge App | iOS 15 and above. Android 11 and above. Works on devices with as little as 2GB RAM. | Tested on iPhone SE (iOS 15), Samsung Galaxy A32 (Android 11), Pixel 6 (Android 13). | Judges are volunteers using older devices. App cannot require a new phone. | M
NFR-BRW-003 | Browser | Responsive breakpoints | Fully functional at 375px (mobile), 768px (tablet), 1024px (small desktop), 1440px (standard). | Responsive test at each breakpoint. No horizontal scrolling at 375px. | Paul confirmed mobile-first. Many users are phone-only. | M
SCALABILITY
NFR-SCL-001 | Scalability | Concurrent users | 500 concurrent users without degradation. July announcement: up to 2,000 parks accessing simultaneously. | Load test: 500 concurrent for 30 minutes. Announcement day simulation: 2,000 concurrent. | July is a known traffic spike. System must not fall over on its most important day. | M
EMAIL DELIVERABILITY
NFR-EML-001 | Email | SPF/DKIM/DMARC | All emails pass SPF, DKIM, and DMARC authentication checks. Sending domain correctly configured to pass council spam filters. | MXToolbox check before go-live. Test to council email address (@manchester.gov.uk). | Council email blocking is a critical known issue. Judges miss allocations. | M
DATA RETENTION
NFR-RET-001 | Retention | Assessment records | Assessment records (scores, feedback, photos, plans) retained 7 years minimum. Certificates retained permanently. | Retention schedule implemented. GDPR-compliant deletion for personal data outside period. | GDPR accountability. Historic context for assessors. KBT reporting obligations. | M
NFR-RET-002 | Retention | Personal data | Personal data deleted within 30 days of account closure. Exception: financial records (7 years), audit log (5 years). | Deletion process documented and tested. Data subject request process documented. | Legal GDPR obligation. | M
SIGN-OFF — 04 — Non-Functional Requirements
Prepared by | Rae (Raemelu Imasiku) — Project Manager, OJ Solutions
Reviewed by | Jonathan Falade — Managing Director, OJ Solutions
Approved by (KBT) | [KBT Product Owner — TBC]
Date approved | ____________
Version | 1.1

## 05 Award Types
SECTION 05 — AWARD TYPE SPECIFICATIONS ¦ All Four Award Tracks
Each track has a different application form, assessment form, scoring model, judge requirements, and pricing. Every difference documented here.
Field | Green Flag Award (Standard) | Community Award | Green Heritage Accreditation | Group Award
OVERVIEW
Description | Primary Green Flag Award. Publicly accessible, free-entry parks. Annual. Valid 12 months. | Separate award recognising community involvement in managing green space. | Additional accreditation bolt-on for historic sites holding Green Flag Award. | For organisations managing 10+ parks. Group-level assessment. Peer review every 2 years.
Status this spec | Fully confirmed in session | Criteria document outstanding | Criteria document outstanding | Deep dive session required before Sprint 2
Combined with | N/A — base award | Standalone | Must hold Green Flag Award first | Each site still receives annual mystery shops
ELIGIBILITY
Site access | Publicly accessible without appointment | Community-managed. May have restricted access. | Must hold or be applying for Green Flag | Organisation must manage 10+ eligible sites
Entry fee | Free to enter | Free or low-cost community access | As per Green Flag Award | As per Green Flag Award
Minimum size | TBC with KBT — likely 0.5 hectares | TBC with KBT | As per Green Flag Award | As per Green Flag Award
APPLICATION FORM
Standard sections apply? | Yes — all standard sections | Adapted sections. Community focus fields added. | Yes — all standard sections plus heritage section | Simplified — no annual management plan. Self-assessment uploaded instead.
Additional sections | None | Community engagement data, volunteer hours, community governance | Heritage significance statement, conservation plan | Organisation-level self-assessment. Annual site list confirmation.
Management plan required? | Yes — Full Assessment years. Not required for Mystery Shop years. | TBC with KBT | Yes — plus conservation plan if applicable | No — replaced by organisation self-assessment
Annual form refresh | Full re-entry. Previous year data pre-populated. | Full re-entry. | As per Green Flag Award | Simplified — contact details check and updated self-assessment only
ASSESSMENT
Assessment types available | Full (Announced) + Mystery Shop alternating | TBC with KBT | Full (Announced) only | Mystery Shop annually per site + Peer Review every 2 years
Number of criteria | 8 criteria | 24 criteria (different model — TBC) | 8 standard + heritage overlay (TBC) | 8 standard assessed at organisation level
Desk assessment? | Yes — Criterion 8. Minimum: 15/30 | TBC with KBT | Yes — includes conservation plan review | Yes — at organisation level
Site assessment? | Yes — Criteria 1-7. Minimum: 42/70 | TBC with KBT | Yes — includes heritage feature inspection | Random sample per peer review visit
Overall pass mark | 66/100 overall AND desk minimum 15 | TBC with KBT | TBC with KBT | TBC with KBT
Band scoring? | Yes — exact bands TBC with KBT | TBC with KBT | TBC with KBT | TBC with KBT
JUDGE REQUIREMENTS
Required judge type | J-01 (Lead) or J-02 (Standard) | J-03 (Community Award Assessor) | J-04 (Green Heritage Assessor — heritage qualification required) | J-01 (Lead) for peer review. J-02 for mystery shops.
Judges per assessment | 1 or 2 (see allocation rules) | TBC with KBT | 2 minimum | 2 for peer review. 1 for mystery shop.
CERTIFICATE & AWARD
Certificate validity | 12 months from issue date | 12 months (TBC) | 12 months — aligned with Green Flag Award | 12 months per site
Public map pin | Green flag pin | Pin type TBC | Heritage pin variant (TBC) | Individual site pins
PRICING
Fee structure | By park type and size band — full schedule pending from KBT Finance | TBC with KBT | Additional fee on top of standard (TBC) | Different pricing structure — TBC with KBT Finance
Consolidated invoicing | Available for multi-park organisations | N/A | Included with standard invoice | Single invoice per organisation
OUTSTANDING FROM KBT
What is needed | Nothing — fully confirmed in session | Complete 24-criteria scoring document from Programme team | Heritage criteria overlay document. Contact: Historic England / Paul. | Full deep-dive session before Sprint 2. Application form, peer review process, pricing all TBC.
SIGN-OFF — 05 — Award Type Specifications
Prepared by | Rae (Raemelu Imasiku) — Project Manager, OJ Solutions
Reviewed by | Jonathan Falade — Managing Director, OJ Solutions
Approved by (KBT) | [KBT Product Owner — TBC]
Date approved | ____________
Version | 1.1

## 19 Open Items
SECTION 19 — OPEN ITEMS & ASSUMPTIONS
Items requiring a decision or input from KBT. Assumptions OJ Solutions has made — KBT should confirm or correct.
ID | Area | Item | What it blocks | KBT Owner | Required by | Status
CRITICAL — Blocks Build
OI-001 | Scoring | Complete scoring criteria — all 8 criteria, sub-criteria, scoring guidance, and band definitions for applicants. | Assessment form cannot be designed or built. Most critical missing document. | Paul | 8 April 2026 | PENDING KBT INPUT
OI-002 | Scoring | Community Award scoring criteria — all 24 criteria. | Community Award application and assessment form cannot be built. | Programme Team | 8 April 2026 | PENDING KBT INPUT
OI-003 | Scoring | Band score definitions — what score range does each band represent? | Results display cannot be built. Parks cannot be shown their score. | Paul | 8 April 2026 | PENDING KBT INPUT
OI-004 | Allocation | Full judge allocation rules — all conditions for 1 vs 2 vs 3 judges per country. | Allocation engine and judge count auto-suggestion cannot be finalised. | Paul | 8 April 2026 | PENDING KBT INPUT
OI-005 | Allocation | Is the judge distance threshold fixed nationally or configurable per country and region? | Distance filter in allocation algorithm. | Paul | 8 April 2026 | PENDING KBT INPUT
OI-006 | Allocation | Is the second judge requirement based on park size, site complexity, admin flag, or a combination? | requires_second_judge flag cannot be set by a deterministic rule without this. | Paul | 8 April 2026 | PENDING KBT INPUT
OI-007 | Allocation | Who holds the current conflict of interest register and in what format? | Existing COI declarations cannot be migrated. | Paul / Lorraine | 8 April 2026 | PENDING KBT INPUT
OI-008 | Governance | Named KBT Product Owner with authority to approve requirements and sign off sprint deliverables. | Project cannot progress past initiation. Sprint sign-offs have no authority. | Anthony | 8 April 2026 | PENDING KBT INPUT
IMPORTANT — Needed Soon
OI-009 | Payments | Full fee schedule — park type and size band matrix, all countries, VAT treatment. | Application form cannot display fee. Invoice cannot be generated. | KBT Finance | 8 April 2026 | PENDING KBT INPUT
OI-010 | Payments | Is KBT Finance comfortable with Stripe as the payment gateway? | If not Stripe, alternative must be agreed before payments module is built. | KBT Finance / Anthony | 8 April 2026 | PENDING KBT INPUT
OI-011 | Payments | Business Central integration — data format and API details. | Invoice data cannot be sent to finance system. | KBT Finance | 15 April 2026 | PENDING KBT INPUT
OI-012 | Access | Super admin or test credentials for the current portal. | Technical team cannot complete architecture review. | Paul / Anthony | 8 April 2026 | PENDING KBT INPUT
OI-013 | Contract | Signed contract to be received by OJ Solutions. | Formal project mandate. Anthony confirmed expected this week. | Anthony | 8 April 2026 | IN PROGRESS
OI-014 | Heritage | Green Heritage Accreditation criteria — full overlay document. | Heritage assessment form cannot be built. | KBT / Historic England | 15 April 2026 | PENDING KBT INPUT
Sessions Required
OI-015 | Group Award | Full deep-dive session for Group Award. Application form, self-assessment, peer review, mystery shops, pricing. | Group Award cannot be built without this session. | Paul / Anthony | Before Sprint 2 | SESSION TO BOOK
OI-016 | Expenses | Judge expenses deep dive — fields, approval flow, finance system feed, consolidated vs per-site. | Expense module cannot be built. | Lorraine / KBT Finance | Before Sprint 2 | SESSION TO BOOK
OI-017 | Reporting | All required reports, fields, MHCLG obligations, automated delivery. | Reporting module cannot be specced. | Lorraine / Paul | Before Sprint 2 | SESSION TO BOOK
Architecture Questions
OI-018 | Architecture | Can a park submit a full assessment in the same year they are receiving a mystery shop? | Data model unique constraint design. | Paul | 8 April 2026 | PENDING KBT INPUT
OI-019 | Architecture | Can a mystery shop result in a conditional award or is it binary — confirm or withdraw? | Decision outcome enum in data model. | Paul | 8 April 2026 | PENDING KBT INPUT
OI-020 | Architecture | What happens to a mystery shop episode if the park withdraws from the programme mid-year? | State machine withdrawal path. | Paul | 8 April 2026 | PENDING KBT INPUT
Assumptions for KBT to Confirm
ASM-001 | Architecture | ASSUMPTION: Cloud hosting (AWS or equivalent). No on-premise or government-specific hosting requirements. | On-premise would significantly increase complexity and cost. | Anthony | 8 April 2026 | PLEASE CONFIRM
ASM-002 | Architecture | ASSUMPTION: No integration with council IT systems (Active Directory, SSO). Parks and judges log in with individual credentials. | Council SSO is complex and slow. Paul confirmed councils have security barriers. | Anthony | 8 April 2026 | PLEASE CONFIRM
ASM-003 | Accessibility | ASSUMPTION: WCAG 2.1 AA standard (not AAA). AAA is significantly more restrictive. | WCAG AAA affects colour, timing, and language complexity requirements. | Anthony | 8 April 2026 | PLEASE CONFIRM
ASM-004 | Payments | ASSUMPTION: Phase 1 payment confirmation is manual (admin marks as paid). Full gateway automation in Phase 2. | Full automation in Phase 1 may be too complex for July go-live. | Anthony / Finance | 8 April 2026 | PLEASE CONFIRM
ASM-005 | Data Migration | ASSUMPTION: All existing park and assessor data can be exported from the current system in a structured format. | If data cannot be exported, manual re-entry required — significant timeline risk. | Paul / Anthony | 8 April 2026 | PLEASE CONFIRM

## INT Pain Points
PAIN POINTS — INTERNAL USE ONLY ¦ NOT SHARED WITH CLIENT
32 pain points from the session. Every problem with the current system. Severity rated. Linked to requirements that solve them.
# | Area | Affects | Pain Point (Current System) | Current Workaround | Sev. | To-Be Solution → links to REQ ID
CRITICAL 🔴
1 | Admin Dashboard | KBT Admin | No admin dashboard. Daily: check inbox + 3 spreadsheets + call colleagues. Takes 30-45 min every morning. | Manual inbox review + spreadsheets | 🔴 | REQ-ADM-001: Real-time dashboard with work queue, alerts, SLA tracking.
2 | Park Registration | KBT Admin | Parks registered with no postcode/region/address. Must Google every new registration. | Manual Google search per registration | 🔴 | REQ-REG-005: Postcode auto-fill. REQ-REG-007: Map pin with OS Greenspace suggestion.
3 | Park Registration | KBT Admin | Organisation name free-typed — hundreds of variants. Makes all government reporting inaccurate. | Admin manually standardises | 🔴 | REQ-REG-XXX: Controlled list — parks select, cannot free-type.
4 | Application Form | All Parks | Cannot save part-way through a page. Parks lose data if they navigate away. | Parks told to complete in one sitting | 🔴 | REQ-APP-001: Auto-save after every field.
5 | Application Form | All Parks | Two browser tabs open on same account corrupts data. | Parks told not to open two tabs | 🔴 | REQ-APP-XXX: Session-level locking per application.
6 | Application Form | All Parks | Management plan re-upload with same filename does not replace. Wrong version assessed. | Parks told to rename file | 🔴 | REQ-APP-003: File hash check — confirms replacement has occurred.
7 | Application Form | All Parks | 10MB limit too low. Plans over 10MB due to photos. | Adobe compression + manual email | 🔴 | REQ-APP-002: 50MB chunked upload + URL link option.
8 | Assessment Types | KBT Admin | Mystery shop tracking in Excel. 5-8% error rate. Wrong type assigned to parks. | Manual cross-reference at season start | 🔴 | REQ-CYC-001: Auto-calculated cycle_type. Replaces spreadsheet entirely.
9 | Judge Allocation | KBT Admin | COI filtering broke — conflicted judges appear in allocation lists. | Manual cross-reference every allocation | 🔴 | REQ-ALO-002: Reliable server-side COI check. Hard blocks never appear.
10 | Results | KBT Admin | Releasing Full results requires clicking ~900 individual buttons. | Admin takes turns clicking all day | 🔴 | REQ-SCR-004: Batch release with date/time. One action.
11 | Judge Feedback | KBT Admin | Feedback is a Word document emailed between judges. Often incomplete, late, inconsistent. | Complex manual coordination | 🔴 | REQ-SCR-006: Typed into structured form. Low score triggers mandatory recommendation.
12 | Invoicing | KBT Admin / Finance | 1,800 invoices per year manually created in Excel and emailed individually. | ~1,800 manual invoices | 🔴 | REQ-PAY-001: Auto-generated on submission.
13 | Security | All | No MFA. Username/password only. Shared credentials in some cases. | No workaround | 🔴 | REQ-SEC-001: MFA for all admin accounts.
HIGH 🟠
14 | Application Form | KBT Admin | Cannot see application progress until submitted. Must log in AS the park. | Takes 5 min per park. Regular occurrence. | 🟠 | REQ-APP-006: Admin sees in-progress applications with % completion. No impersonation.
15 | Application Form | All Parks | Address amendment mid-form loses all data. | Amend → exit → re-enter → navigate back | 🟠 | REQ-APP-001: Auto-save on every field change.
16 | Judge Allocation | KBT Admin | Cannot see which parks have only 1 judge accepted vs intended 2. | Manual report + cross-reference | 🟠 | REQ-ALO-XXX: Allocation dashboard shows 0/1/2 judges per site at a glance.
17 | Judge Allocation | KBT Admin | Emails to judges blocked by council firewalls. Judges never receive allocations. | KBT manually calls or uses personal emails | 🟠 | REQ-NOT-002: SMS backup notifications. NFR-EML-001: Correct SPF/DKIM hosting.
18 | Judge Portal | Judges | Not mobile-responsive. Judges use paper forms on site. Type up at home = 2-4 hours admin per visit. | Paper forms + photos on personal phone + typed at home | 🟠 | REQ-JDG-001: Fully mobile-responsive. REQ-SCR-003: Score + photo + voice on mobile.
19 | Invoicing | Finance | PayPal does not generate proper receipts. Manual tracking. | Manual spreadsheet | 🟠 | REQ-PAY-003: Stripe integration with proper receipts.
20 | Security | All | Password reset emails blocked by firewalls. Admin looks up and emails passwords — GDPR risk. | Admin emails plain text passwords | 🟠 | REQ-SEC-001: Correct hosting. Proper reset flow. Admin cannot see passwords.

## INT Action Tracker
ACTION TRACKER — INTERNAL USE ONLY
All actions. All owners. All due dates. Bank holidays: Good Friday 4 April + Easter Monday 7 April. First working day back: Tuesday 8 April.
# | Owner | Action | Due | Priority | Status
OJ SOLUTIONS
1 | Rae | Send KBT written session summary and this requirements specification. Confirm what was understood, what is outstanding, what is needed from them. | 8 April 2026 | CRITICAL | NOT STARTED
2 | Rae | Schedule four follow-up sessions: Group Award, Judge Expenses, Reporting, Finance. All before 21 April. | 8 April 2026 | CRITICAL | NOT STARTED
3 | Rae | Send KBT list of all email templates required with draft copy for approval. | 15 April 2026 | HIGH | NOT STARTED
4 | Rae | Chase KBT charity registration number (Anthony) for What3Words NGO pricing. | 8 April 2026 | HIGH | NOT STARTED
5 | Rae | Update RAID tracker with new risks and dependencies from session + technical analysis. | 8 April 2026 | HIGH | NOT STARTED
6 | Richard | Finalise dual application window data model. 3 architecture questions to KBT outstanding (OI-018-020). | 14 April 2026 | CRITICAL | IN PROGRESS
7 | Richard | Finalise judge allocation engine once OI-004 to OI-007 answered by KBT. | After KBT answers | CRITICAL | BLOCKED — awaiting KBT input
8 | Richard | Confirm OS Open Greenspace licence for charitable/commercial web app use. Begin PostGIS import setup. | 11 April 2026 | HIGH | NOT STARTED
9 | Richard | Begin What3Words JS SDK integration in dev environment. Working widget demo for KBT. | 18 April 2026 | HIGH | NOT STARTED
10 | Oya | Begin wireframe design: organisation dashboard, park registration, application form, judge allocation with map. Based on confirmed requirements. | 18 April 2026 | HIGH | NOT STARTED
KBT ACTIONS
11 | Paul (KBT) | Send complete scoring criteria — all 8 criteria, sub-criteria, scoring guidance, band definitions. Most critical document. | 8 April 2026 | CRITICAL | OUTSTANDING
12 | Paul (KBT) | Send judge allocation rules — all conditions for 1 vs 2 vs 3 judges. | 8 April 2026 | CRITICAL | OUTSTANDING
13 | Programme Team | Send Community Award scoring criteria — all 24 criteria. | 8 April 2026 | CRITICAL | OUTSTANDING
14 | Paul / Lorraine | Send example completed judge scoring form and feedback report. | 8 April 2026 | CRITICAL | OUTSTANDING
15 | Paul / Lorraine | Confirm COI register — format and location. | 8 April 2026 | CRITICAL | OUTSTANDING
16 | Anthony | Name KBT Product Owner with sign-off authority. | 8 April 2026 | CRITICAL | OUTSTANDING
17 | Paul / Anthony | Provide portal access — super admin or test credentials. | 8 April 2026 | HIGH | OUTSTANDING
18 | KBT Finance | Confirm full fee schedule — all types, bands, countries, VAT. | 8 April 2026 | CRITICAL | OUTSTANDING
19 | Anthony | Signed contract. Expected this week. Bank holidays 4 and 7 April. | 8 April 2026 | CRITICAL | IN PROGRESS
20 | Paul | Answer OI-018, OI-019, OI-020 (architecture questions). | 8 April 2026 | CRITICAL | OUTSTANDING
21 | Anthony | Confirm KBT charity registration number for What3Words pricing. | 8 April 2026 | HIGH | OUTSTANDING